## 📋 Overview
🎓 FYP MASTER PLANNER – AI Insurance Projects
Project 7: AI Risk Dashboard ¦ Project 8: Synthetic Data Marketplace ¦ Team: 3 Members
PROJECT 7 – AI Risk Dashboard |  |  | PROJECT 8 – Synthetic Data Marketplace
• Interactive risk metrics dashboard • Loss simulation engine • Synthetic Pakistani insurance data • Python + Streamlit/Dash frontend • ML-based risk scoring • Visualisations & KPI cards |  |  | • GAN-based synthetic data generator • Multi-use-case platform (pricing, fraud, reserving) • Performance benchmarking vs real data • Web platform concept + live demo • Business model / startup pitch layer • API-ready data marketplace UI
👥 TEAM MEMBERS & COLOUR CODE
🔵 Member 1 – Data / ML Lead |  | 🟢 Member 2 – Backend / Analytics |  | 🟠 Member 3 – Frontend / PM / Research
Synthetic data (GANs), ML models, data pipelines, Python backend |  | Risk metrics engine, loss simulation, statistical models, Flask/FastAPI |  | Streamlit/Dash UI, research docs, presentation, README, project mgmt
📅 TIMELINE SUMMARY
Phase | Timeline | Description |  |  | Status
Phase 1 | Week 1-2 | Research, Data Collection & Setup |  |  | Haven't Started Yet
Phase 2 | Week 3-4 | Core Development – Models & Backend |  |  | Haven't Started Yet
Phase 3 | Week 5-6 | Frontend, Dashboard & Platform Build |  |  | Haven't Started Yet
Phase 4 | Week 7-8 | Integration, Testing & Refinement |  |  | Haven't Started Yet
Phase 5 | Week 9-10 | Documentation, Presentation & Polish |  |  | Haven't Started Yet
|  | If asked "where is your data from?" you say: "We use synthetic data generated via CTGAN, calibrated against publicly available SECP industry statistics and benchmark actuarial datasets. This approach is privacy-preserving, scalable, and is itself one of the core contributions of our research." |  | you do NOT need real company data ✅ Your projects are specifically designed around synthetic data — that's actually the whole point of Project 8, and Project 7 uses synthetic data as input. This is one of the strongest selling points of your FYP.

## 📅 Day-by-Day Plan
📅 DAY-BY-DAY TASK PLANNER ¦ 10-Week FYP Roadmap
Day / Date | Phase | Tasks (Detailed Steps) | Member 1 🔵 (Data/ML) | Member 2 🟢 (Backend) | Member 3 🟠 (Frontend/PM) | Status
Day 1 Mon | Phase 1 Research & Setup | • Kickoff meeting: divide ownership of P7 & P8 • Set up GitHub repo (branching strategy: main/dev/feature) • Install tools: Python 3.10+, VS Code, Jupyter, Git • Create shared Google Drive folder structure • Draft project scope document (1-page each project) | Set up Python env: install pandas, numpy, torch, scikit-learn, matplotlib | Install Flask/FastAPI, PostgreSQL; set up local DB | Create Notion/Trello board, draft 1-page scope for both projects | Pending
Day 2 Tue | Phase 1 Research & Setup | • Deep research: Pakistani insurance market (SECP reports, SBP data) • Study GAN architectures: CTGAN, TVAE, CopulaGAN • Identify 5-7 key risk metrics used by Pakistani insurers • Research Streamlit vs Dash for dashboard | Read 3 GAN papers: CTGAN (Xu 2019), TVAE, CopulaGAN. Take notes on architectures | List 10 risk KPIs: loss ratio, combined ratio, CAT loss, reserve adequacy etc. | Research SECP website, gather 2022-24 annual reports of top 5 Pakistani insurers | Pending
Day 3 Wed | Phase 1 Research & Setup | • Design synthetic data schema for insurance datasets • Define columns: policy_id, premium, claims, age, region, vehicle_type, fraud_flag etc. • Research real Pakistani loss distributions (Pareto, LogNormal) • Map out P8 platform architecture (frontend, API, data storage) | Design schema: 25-30 columns for auto/health/property insurance. Write schema.json | Research actuarial loss distributions; write distribution_notes.md | Sketch wireframe of P7 dashboard (paper or Figma free) – 5 screens | Pending
Day 4 Thu | Phase 1 Research & Setup | • Generate baseline synthetic data using numpy/scipy (before GAN) • Set up project folder structure for both projects • Create requirements.txt and README.md • Weekly sync: share research findings | Write generate_baseline_data.py: create 10,000 rows synthetic data using scipy distributions | Create project directory structure, write base README.md for both projects | Document research findings in shared Google Doc; set up project wiki | Pending
Day 5 Fri | Phase 1 Research & Setup | • Review Day 1-4 work, merge all branches to dev • Supervisor meeting prep: prepare questions • Set milestones for Week 2 • EDA on any real-world insurance datasets found online (Kaggle) | Run EDA on Kaggle insurance dataset (exploratory_analysis.ipynb) | Validate baseline synthetic data statistics vs real-world benchmarks | Prepare supervisor meeting slides (5 slides: problem, approach, timeline, team, questions) | Pending
Day 6 Mon | Phase 1 Data & Models | • Install and test SDV library (Synthetic Data Vault) • Begin CTGAN training on baseline data • Research fraud detection features for P7 dashboard • Define KPI formulas: loss ratio = claims/premium | pip install sdv; run CTGAN on baseline_data.csv; log training metrics | Implement KPI calculation functions in metrics.py (loss_ratio, combined_ratio, CAT_loss) | Research fraud indicators in Pakistani insurance; list 8-10 fraud red flags | Pending
Day 7 Tue | Phase 1 Data & Models | • Generate first GAN-based synthetic dataset (auto insurance) • Evaluate quality: statistical similarity, Wasserstein distance • Begin loss simulation model design (Monte Carlo basics) • Research reserving methods: Chain Ladder, Bornhuetter-Ferguson | Train CTGAN for 300 epochs; generate 50,000 synthetic rows; compute fidelity scores | Research Chain Ladder method; write chain_ladder.py stub | Design P8 marketplace UI wireframe (Figma or draw.io): homepage, dataset catalog, API docs page | Pending
Day 8 Wed | Phase 1 Data & Models | • Expand synthetic data: add health insurance schema • Implement Monte Carlo loss simulation (1000 iterations) • Set up Flask API skeleton (endpoints: /api/metrics, /api/simulate) • Data validation: check for data leakage, anomalies | Write ctgan_health.py; train model on health insurance schema; validate distributions | Implement monte_carlo_simulation.py: simulate 1000 loss scenarios with seed control | Set up basic Flask app structure: app.py, routes.py, static/, templates/ | Pending
Day 9 Thu | Phase 1 Data & Models | • Generate property/fire insurance synthetic data (3rd dataset) • Connect Monte Carlo to KPI metrics • Build basic API response structure (JSON) • Prepare Week 2 review for supervisor | Train CTGAN on property insurance schema; merge all 3 datasets into master_synthetic.csv | Connect simulation output to metrics functions; test /api/simulate endpoint | Write progress report (1 page); update Trello/Notion board with % complete | Pending
Day 10 Fri | Phase 1 Data & Models | • Week 2 review & supervisor meeting • Merge all Week 2 branches • Quality check all synthetic datasets • Plan Week 3 development sprint | Run statistical tests: KS-test, chi-squared on synthetic vs baseline; document results | Test all API endpoints; fix bugs; write API documentation draft | Lead supervisor meeting; present data samples and wireframes; record feedback | Pending
Day 11 Mon | Phase 2 Core Dev | • Begin Streamlit dashboard for P7 (main app file) • Implement risk score algorithm (weighted KPI composite) • Improve GAN: try TVAE for comparison • Set up PostgreSQL database for storing simulation results | Train TVAE model; compare fidelity scores CTGAN vs TVAE; document winner | Write risk_score.py: weighted composite of 5 KPIs → single 0-100 risk score | Create streamlit_app.py skeleton; add sidebar navigation, title, layout structure | Pending
Day 12 Tue | Phase 2 Core Dev | • Build KPI cards in dashboard (loss ratio, combined ratio, risk score) • Implement interactive filters (region, insurance type, year) • P8: build dataset generator API endpoint • Database schema design and creation | Write data_loader.py: load synthetic CSV into dashboard dynamically | Create DB schema (PostgreSQL): tables for datasets, simulations, users; run migrations | Build KPI metric cards in Streamlit using st.metric(); add color coding (red/amber/green) | Pending
Day 13 Wed | Phase 2 Core Dev | • Build loss simulation chart (plotly line chart with confidence intervals) • Add geographic heatmap (Pakistan provinces) • P8: implement dataset quality scoring endpoint • User authentication stub for P8 | Generate geo-coded synthetic data with province column; create province_map.py | Implement quality_score.py: compute fidelity, privacy, utility scores for each dataset | Build interactive plotly chart in Streamlit; add confidence interval bands (5th/95th percentile) | Pending
Day 14 Thu | Phase 2 Core Dev | • Build fraud detection visualization (scatter plot, anomaly highlighting) • Implement 'What-If' simulator UI in dashboard • P8: build dataset comparison endpoint (synthetic vs real stats) • Weekly integration test | Implement anomaly detection: Isolation Forest on synthetic data; flag top 5% as fraud | Build /api/compare endpoint: returns statistical diff table between 2 datasets | Add fraud scatter plot to dashboard; add What-If slider widgets (st.slider) | Pending
Day 15 Fri | Phase 2 Core Dev | • Week 3 integration: connect all P7 components end-to-end • Demo run: full dashboard walkthrough • Document all APIs • Plan Week 4: P8 platform front-end | Ensure all data flows: GAN output → API → Streamlit dashboard; fix data type issues | Full API test suite; document all endpoints in api_docs.md | Record 5-min demo video of dashboard; share with supervisor for feedback | Pending
Day 16 Mon | Phase 2 Core Dev | • Begin P8 web platform frontend (React or Streamlit multi-page) • Implement dataset catalog page (list, filter, download) • Advanced GAN: add conditional generation (by region/product) • Set up user registration/login for P8 | Implement conditional CTGAN: add conditioning on region and insurance_type columns | Build /api/datasets endpoint: list all available synthetic datasets with metadata | Build P8 homepage and dataset catalog page in Streamlit/React | Pending
Day 17 Tue | Phase 2 Core Dev | • Build P8 data preview page (sample rows, statistics) • Implement pricing use case demo (GLM on synthetic data) • Add download functionality to P8 • Privacy evaluation: check synthetic data for re-identification risk | Run Generalized Linear Model (GLM) on synthetic auto data for premium pricing; document results | Implement privacy evaluation: nearest-neighbor distance ratio; write privacy_report.py | Build dataset detail/preview page: show 10 sample rows, key stats, column descriptions | Pending
Day 18 Wed | Phase 2 Core Dev | • Implement fraud detection use case demo (Random Forest on synthetic data) • Reserving use case: Chain Ladder on synthetic claims triangle • Build P8 use-case showcase page • Performance comparison: model trained on synthetic vs real data | Train Random Forest fraud classifier; report precision/recall/F1; compare synthetic vs real | Implement chain_ladder_complete.py; generate claims development triangle; compute IBNR | Build use-case page with 3 tabs: Pricing / Fraud / Reserving with charts | Pending
Day 19 Thu | Phase 2 Core Dev | • Build P8 API documentation page (interactive) • Add business model section to P8 (subscription tiers mockup) • Improve P7 dashboard: add historical trend charts • End-to-end test both projects | Add API key generation stub to P8 backend; simulate API call in Jupyter notebook | Build historical trend line charts for P7 (5-year simulated loss trend) | Design business model page for P8: Free / Pro / Enterprise tiers; design pricing table | Pending
Day 20 Fri | Phase 2 Core Dev | • Week 4 review: both projects should have working prototypes • Supervisor demo • Identify top 5 bugs/improvements for Week 5 • Update README and project documentation | Write technical report section: GAN architecture, training details, evaluation metrics | Write technical report section: API design, simulation methodology, risk metrics | Update both READMEs; create bug tracking list; prepare supervisor demo | Pending
Day 21 Mon | Phase 3 UI Polish | • UI redesign pass: improve P7 dashboard aesthetics • Add dark/light mode toggle to P7 • Improve GAN training: increase epochs, tune hyperparameters • Add loading spinners and error handling to both apps | Retrain CTGAN with 500 epochs and tuned hyperparameters; compare fidelity improvement | Add error handling to all API endpoints; implement try/except with proper HTTP status codes | Redesign P7 dashboard: custom CSS/theme, improve color scheme, add logo placeholder | Pending
Day 22 Tue | Phase 3 UI Polish | • Add export functionality: download charts as PNG, data as CSV • Implement alert system in P7 (flag insurers with risk score > 70) • Build P8 data generation wizard (step-by-step UI) • Add tooltips and help text throughout both apps | Implement data_exporter.py: export synthetic datasets in CSV, JSON, Parquet formats | Build alert engine: send email/notification stub when risk threshold breached | Build 3-step data generation wizard in P8: Step1: Choose type → Step2: Params → Step3: Download | Pending
Day 23 Wed | Phase 3 UI Polish | • Add user onboarding/tutorial overlay to both apps • Implement caching for API responses (Redis or simple dict cache) • P7: add peer comparison feature (compare 2 insurers side by side) • Performance optimization: reduce dashboard load time | Add @st.cache_data to expensive data loading functions; measure load time improvement | Implement simple in-memory cache for API; add cache headers | Build insurer comparison widget in P7: select 2 companies → side-by-side KPI table | Pending
Day 24 Thu | Phase 3 UI Polish | • Mobile responsiveness check for both apps • Add about/documentation page to both apps • Complete P8 marketplace concept: add 'ratings' and 'reviews' mockup • Stress test: generate 500,000 row synthetic dataset | Test CTGAN scalability: generate 500K rows; measure time and memory; optimize if needed | Add /api/health endpoint; write deployment guide (Docker instructions) | Build About page for both apps; add team bios, project description, tech stack badges | Pending
Day 25 Fri | Phase 3 UI Polish | • Week 5 review: UI/UX complete • Both apps deployable locally end-to-end • Write deployment instructions • Plan final 5 weeks: documentation + presentation | Create Docker setup: write Dockerfile for GAN service | Create Docker setup: write Dockerfile for API service; test docker-compose | Deploy both apps on Streamlit Cloud or Heroku (free tier); share public URLs | Pending
Day 26 Mon | Phase 3 Integration | • Full system integration test: GAN → API → Dashboard • Write integration test scripts • Fix all critical bugs from Week 5 testing • Add logging to all services | Write test_gan.py: unit tests for data generation and quality checks | Write test_api.py: automated tests for all 10+ API endpoints using pytest | Write test_ui.py: Selenium smoke tests for dashboard (if time allows); else manual test plan | Pending
Day 27 Tue | Phase 3 Integration | • Security review: sanitize inputs, add rate limiting to P8 API • Add data versioning to P8 (track dataset versions) • Improve visualization quality: publication-ready charts • Code review session (peer review all code) | Code review M2 and M3 code; raise GitHub PRs with comments | Add rate limiting to Flask API (flask-limiter); add input validation | Improve all charts: proper titles, axis labels, legends, source attribution | Pending
Day 28 Wed | Phase 3 Integration | • Begin FYP report writing (LaTeX or Word) • Chapter 1: Introduction, Problem Statement, Objectives • Chapter 2: Literature Review (10-15 papers) • Divide report chapters among team | Write Literature Review section: 5 papers on GANs for tabular data synthesis | Write Literature Review section: 5 papers on insurance risk metrics and dashboards | Write Introduction chapter; set up LaTeX/Word template; manage bibliography (Zotero) | Pending
Day 29 Thu | Phase 3 Integration | • Report: Chapter 3 – Methodology • Describe GAN architecture, training process, evaluation metrics • Describe risk metrics formulas, simulation methodology • Add system architecture diagram | Write GAN methodology: architecture diagram, training loop, hyperparameter table | Write simulation methodology: Monte Carlo setup, distribution assumptions, KPI formulas | Draw system architecture diagrams (draw.io); insert into report; format figures | Pending
Day 30 Fri | Phase 3 Integration | • Week 6 review: integration complete, report 30% done • Update supervisor with progress • Resolve any remaining integration issues • Plan Weeks 7-10: results, evaluation, final report, presentation | Document GAN evaluation results: fidelity table, Wasserstein distances, KS-test p-values | Document API performance: response times, uptime, endpoint coverage | Prepare Week 6 supervisor update; update project Gantt chart | Pending
Day 31 Mon | Phase 4 Results | • Report: Chapter 4 – Implementation Details • Code walkthroughs documented • Capture all screenshots for report • Run final model evaluations | Write GAN implementation section; add code snippets; capture training loss plots | Write API implementation section; document database schema; add ER diagram | Capture 20+ dashboard/platform screenshots; annotate and label for report | Pending
Day 32 Tue | Phase 4 Results | • Report: Chapter 5 – Results and Evaluation • Quantitative results: fidelity scores, model accuracy • Qualitative results: dashboard usability • Add all result tables and charts | Create results table: CTGAN vs TVAE vs baseline on 5 fidelity metrics | Create performance table: API latency, simulation accuracy vs actuarial benchmarks | Create usability summary; add dashboard screenshots with annotations to report | Pending
Day 33 Wed | Phase 4 Results | • Comparative analysis: synthetic data performance vs real data • P8: demonstrate all 3 use cases with quantitative results • Report: add discussion section • Run additional experiments if needed | Run final experiment: train 3 ML models on synthetic data; compare to real data baseline | Run Chain Ladder on synthetic vs industry benchmarks; compute error percentage | Write discussion section: interpret results, limitations, future work | Pending
Day 34 Thu | Phase 4 Results | • Report: Chapter 6 – Conclusion • Future work section • References and bibliography (20+ sources) • Abstract and Executive Summary | Proofread technical sections; verify all formulas in report are correct | Proofread methodology and results; check all citations | Write abstract (250 words); write conclusion chapter; compile full bibliography | Pending
Day 35 Fri | Phase 4 Results | • Report draft complete (first full draft) • Internal peer review: each member reviews others' chapters • Supervisor submission of draft • Plan final polishing weeks | Review entire report for technical accuracy; mark corrections | Review report formatting, figures, tables, page numbering | Compile full report PDF; submit to supervisor; collect feedback form | Pending
Day 36 Mon | Phase 4 Refinement | • Act on supervisor report feedback • Polish code: add docstrings, remove debug code • Prepare GitHub repository for submission • Write CONTRIBUTING.md and LICENSE | Add docstrings to all Python functions; run pylint; fix linting issues | Clean API code; add type hints; generate automatic API docs with Swagger/FastAPI docs | Polish GitHub README: add badges, demo GIF, installation guide, screenshots | Pending
Day 37 Tue | Phase 4 Refinement | • Begin presentation slides (PowerPoint/Google Slides) • Slide structure: problem, solution, demo, results, team • Prepare live demo script • Practice timing: aim for 15-min presentation | Prepare demo of GAN training and synthetic data generation (Jupyter notebook demo) | Prepare API demo: Postman collection or live API call during presentation | Build presentation slides (20 slides); design theme matching project colors | Pending
Day 38 Wed | Phase 4 Refinement | • First full presentation rehearsal • Time each section • Prepare answers to common questions • Record rehearsal video for review | Prepare technical Q&A: GAN architecture questions, privacy concerns, scalability | Prepare technical Q&A: actuarial accuracy, simulation assumptions, API design choices | Lead rehearsal session; record video; note improvements; time each section | Pending
Day 39 Thu | Phase 4 Refinement | • Final report edits based on peer and supervisor feedback • Finalize all code and freeze GitHub repo • Prepare project poster (A1 size) • Final data export: zip all datasets, models, notebooks | Zip and archive all model weights, synthetic datasets, training notebooks | Final API deployment check; ensure public URL is stable; test from mobile | Design A1 project poster (Canva or PowerPoint); print and review | Pending
Day 40 Fri | Phase 4 Refinement | • Week 8 review: everything should be DONE except final submission polish • Submit second draft to supervisor • Final Q&A prep session • Buffer day for unexpected issues | Final check: all experiments reproducible; requirements.txt up to date | Final API health check; backup all data to Google Drive | Final presentation rehearsal with timer; prepare physical backup (USB drive with everything) | Pending
Day 41 Mon | Phase 5 Final Polish | • Final report formatting and proofreading • Check: page numbers, table of contents, figure list • Turnitin check / plagiarism check • Bind report if required by university | Final proofread of Chapters 3 & 5 (technical accuracy check) | Final proofread of Chapters 2 & 4; check all references are correctly cited | Format entire report: margins, fonts, spacing, headers; generate final PDF | Pending
Day 42 Tue | Phase 5 Final Polish | • Second full presentation rehearsal (with panel Q&A simulation) • Refine presentation based on rehearsal • Prepare handouts or one-pager summary • Check all demo environments are working | Simulate panel question: 'Why use GAN instead of simple random sampling?' – prepare 2-min answer | Simulate panel question: 'How accurate is your risk model?' – prepare data-backed answer | Simulate panel question: 'What is the business viability of P8?' – prepare startup pitch answer | Pending
Day 43 Wed | Phase 5 Final Polish | • Final submission preparation • Upload all deliverables to university portal • Final GitHub commit with version tag (v1.0.0) • Celebrate milestone! | Final git tag: git tag v1.0.0; push all branches; verify GitHub Actions (if any) pass | Upload API to final hosting; verify all links in report are active | Compile final submission package: report PDF, code ZIP, presentation PDF, poster PDF | Pending
Day 44 Thu | Phase 5 Final | • PRESENTATION DAY PREP • Arrive early; test AV equipment • Final mental rehearsal • Set up demo on presentation laptop • Dress professionally! | Load all demos on presentation laptop; test Jupyter, Streamlit, API locally | Test API on mobile as backup demo; have Postman ready as fallback | Print handouts; bring USB backup; charge all devices; set up presentation room | Pending
Day 45 Fri | Phase 5 Final | 🎓 FYP PRESENTATION DAY! 🎓 • Present both projects to panel • Live demo: dashboard + marketplace • Answer panel questions confidently • Submit all final deliverables | Present GAN + synthetic data generation live demo with confidence | Present risk metrics, simulation, API demo – show quantitative results | Lead presentation narrative; manage time; handle Q&A coordination | Pending

## 🛠️ Resources & Tools
🛠️ RESOURCES, TOOLS & DATA REQUIREMENTS
💻 SOFTWARE & TOOLS
Python 3.10+ | Core programming language | pip install (free) | All members
SDV Library (sdv) | CTGAN, TVAE, CopulaGAN models | pip install sdv | Member 1
PyTorch | Deep learning backend for GANs | pip install torch | Member 1
Scikit-learn | ML models (RF, GLM, Isolation Forest) | pip install scikit-learn | Member 1 & 2
Streamlit | Dashboard & web app framework | pip install streamlit | Member 3
Flask / FastAPI | REST API backend | pip install flask fastapi | Member 2
PostgreSQL | Database for results storage | postgresql.org (free) | Member 2
Plotly | Interactive charts | pip install plotly | Member 3
Pandas / NumPy | Data manipulation | pip install pandas numpy | All members
GitHub | Version control & collaboration | github.com (free) | All members
VS Code | Code editor | code.visualstudio.com (free) | All members
Jupyter Notebook | Data exploration & demos | pip install jupyter | Member 1
Docker | Containerization (optional) | docker.com (free) | Member 2
Figma | UI wireframing | figma.com (free tier) | Member 3
Canva / PowerPoint | Poster & presentation | canva.com (free) | Member 3
Postman | API testing | postman.com (free) | Member 2
Zotero | Reference management | zotero.org (free) | Member 3
Notion / Trello | Project management | notion.so (free) | Member 3
📊 DATA SOURCES
SECP Annual Reports | Insurance sector statistics | secp.gov.pk (free PDF download) | Member 1 & 3
SBP Publications | Pakistan financial data | sbp.org.pk (free) | Member 3
Kaggle Insurance Dataset | Real-world insurance data for comparison | kaggle.com (free) | Member 1
UCI ML Repository | Insurance benchmark datasets | archive.ics.uci.edu (free) | Member 1
Pakistan Bureau of Statistics | Demographic data for synthetic gen | pbs.gov.pk (free) | Member 1
World Bank Pakistan Data | Macro economic indicators | data.worldbank.org (free) | Member 3
OpenStreetMap | Pakistan geographic data for heatmap | openstreetmap.org (free) | Member 2
Swiss Re Sigma Reports | Global insurance loss data | sigma.swissre.com (free PDF) | Member 2
Lloyd's Emerging Risk Reports | Risk benchmarks | lloyds.com (free) | Member 2
📚 KEY PAPERS TO READ
Xu et al. (2019) – CTGAN | Modeling Tabular data using Conditional GAN | arXiv:1907.00503 | Member 1
Park et al. (2018) – Data Synthesis | Data Synthesis based on Generative Adversarial Networks | VLDB 2018 | Member 1
Goodfellow et al. (2014) | Original GAN paper | arXiv:1406.2661 | Member 1
Jorion (2007) – VaR | Value at Risk: The New Benchmark | Book – library | Member 2
England & Verrall – Reserving | Stochastic Claims Reserving in Insurance | British Actuarial Journal | Member 2
Frees (2009) – Loss Models | Regression Modeling with Actuarial Applications | Book – library | Member 2
Assefa et al. (2020) | Generating Synthetic Financial Datasets | arXiv:2002.02842 | Member 1
Koivu et al. (2020) | Synthetic Patient Data in Healthcare | JAMIA | Member 3 – for comparison
EIOPA Reports | EU insurance risk dashboard methodology | eiopa.europa.eu (free) | Member 2
Wuthrich & Merz | Statistical Foundations of Actuarial Learning | Springer (library) | Member 2
✅ DELIVERABLES CHECKLIST
Source Code | GitHub repo with README, requirements.txt, Docker | GitHub (public/private) | All
Synthetic Datasets | 3 datasets: Auto, Health, Property (50K rows each) | CSV / Parquet files | Member 1
GAN Model Weights | Saved .pkl files for CTGAN and TVAE | Model artifacts | Member 1
REST API | 10+ endpoints, documented, deployed | Flask/FastAPI | Member 2
P7 Dashboard | Streamlit app – risk metrics, simulation, fraud viz | Deployed URL | Member 3
P8 Platform | Marketplace UI – catalog, generator, use cases | Deployed URL | Member 3
FYP Report | 50-80 pages, 6 chapters, 20+ references | PDF (submitted) | All
Presentation Slides | 20 slides, 15-min presentation | PowerPoint/PDF | Member 3
Project Poster | A1 size, visual summary | Printed + PDF | Member 3
Jupyter Notebooks | EDA, model training, evaluation demos | GitHub | Member 1
API Documentation | Swagger/Postman collection | Docs page | Member 2
Evaluation Results | Fidelity, privacy, utility scores table | Report Chapter 5 | Member 1

## ✅ Task Tracker
✅ TASK TRACKER – Update Daily
Day | Task Description | Assigned To | Status | Priority
Day 1 | Set up GitHub repository and folder structure | All Members | Pending | 🔴 High
Day 1 | Install all required Python libraries | All Members | Pending | 🔴 High
Day 1 | Create shared Google Drive folder | Member 3 | Pending | 🟡 Medium
Day 2 | Research SECP insurance reports | Member 3 | Pending | 🔴 High
Day 2 | Study CTGAN paper (arXiv:1907.00503) | Member 1 | Pending | 🔴 High
Day 2 | List 10 insurance risk KPIs | Member 2 | Pending | 🔴 High
Day 3 | Design synthetic data schema (25 columns) | Member 1 | Pending | 🔴 High
Day 3 | Sketch P7 dashboard wireframe | Member 3 | Pending | 🟡 Medium
Day 4 | Generate baseline synthetic data (10,000 rows) | Member 1 | Pending | 🔴 High
Day 4 | Create requirements.txt and README | Member 2 | Pending | 🟡 Medium
Day 5 | EDA on Kaggle insurance dataset | Member 1 | Pending | 🟡 Medium
Day 5 | Prepare supervisor meeting slides | Member 3 | Pending | 🔴 High
Day 6 | Train CTGAN model (auto insurance) | Member 1 | Pending | 🔴 High
Day 6 | Implement KPI functions in metrics.py | Member 2 | Pending | 🔴 High
Day 7 | Evaluate GAN quality (KS-test, Wasserstein) | Member 1 | Pending | 🔴 High
Day 7 | Design P8 platform architecture | Member 3 | Pending | 🟡 Medium
Day 8 | Train CTGAN on health insurance data | Member 1 | Pending | 🔴 High
Day 8 | Implement Monte Carlo simulation | Member 2 | Pending | 🔴 High
Day 9 | Generate property insurance synthetic data | Member 1 | Pending | 🔴 High
Day 9 | Build Flask API skeleton | Member 2 | Pending | 🔴 High
Day 10 | Statistical validation of all synthetic datasets | Member 1 | Pending | 🔴 High
Day 11 | Train TVAE model for comparison | Member 1 | Pending | 🟡 Medium
Day 11 | Build risk score algorithm | Member 2 | Pending | 🔴 High
Day 11 | Create Streamlit app skeleton | Member 3 | Pending | 🔴 High
Day 12 | Build KPI metric cards in Streamlit | Member 3 | Pending | 🔴 High
Day 12 | Set up PostgreSQL database | Member 2 | Pending | 🟡 Medium
Day 13 | Add geographic heatmap to dashboard | Member 3 | Pending | 🟡 Medium
Day 13 | Implement privacy evaluation | Member 2 | Pending | 🔴 High
Day 14 | Build fraud detection visualization | Member 3 | Pending | 🟡 Medium
Day 15 | End-to-end demo of P7 dashboard | All Members | Pending | 🔴 High
Day 16 | Implement conditional CTGAN | Member 1 | Pending | 🟡 Medium
Day 17 | GLM pricing model on synthetic data | Member 1 | Pending | 🔴 High
Day 18 | Fraud classifier (Random Forest) | Member 1 | Pending | 🔴 High
Day 18 | Chain Ladder reserving implementation | Member 2 | Pending | 🔴 High
Day 20 | Working prototypes of both P7 & P8 | All Members | Pending | 🔴 High
Day 28 | Start FYP report – Chapter 1 | Member 3 | Pending | 🔴 High
Day 28 | Literature Review – GAN papers | Member 1 | Pending | 🔴 High
Day 35 | First full report draft submitted to supervisor | All Members | Pending | 🔴 High
Day 37 | Presentation slides (20 slides) | Member 3 | Pending | 🔴 High
Day 41 | Final report formatted and proofread | All Members | Pending | 🔴 High
Day 43 | Final submission package uploaded | All Members | Pending | 🔴 High
Day 45 | FYP PRESENTATION | All Members | Pending | 🔴 High
Best of Luck!!